ClickUp to Productive.io

Migration Dry Run

Learnings & Production Migration Plan

Tika Go-Live Space • Sandbox Instance

28 February 2026

# Part 1: MCP Server Learnings

What we discovered about the Productive MCP server during the Tika Go-Live dry run.

## 1. Schema Strictness & Silent Failures

The MCP server uses Zod schemas with .strict() mode. This means any unrecognised field in a request causes an immediate rejection. While this is good for validation, it creates a rigid contract that makes iterative migration harder.

### Specific Issues Encountered

| Issue | Detail | Impact | Severity |
| --- | --- | --- | --- |
| batch create rejects task_list_id | BatchTaskItemSchema doesn’t include task_list_id. Only default_task_list_id on the wrapper. | Forced individual creates (120 API calls instead of ~5 batch calls) | HIGH |
| labels rejected on update | UpdateTaskSchema doesn’t include labels field. Only available on CreateTaskSchema. | Cannot retrospectively tag tasks. Must be set at creation. | WARNING |
| workflow_status silently ignored | If the status name isn’t in productive.config.json, the server logs a warning to stderr but returns success. | Tasks appeared to update but status didn’t change. No error surfaced to caller. | CRITICAL |
| status vs workflow_status naming | Field is workflow_status, not status. The Productive UI shows “Status”. | Initial attempts used wrong field name, rejected by strict schema. | WARNING |
| list_subtasks param name | Tool requires parent_task_id, not task_id. | First call failed; had to check schema. | OK – MINOR |

## 2. Workflow Status Architecture

This was the biggest learning. The Productive.io workflow status system has three layers:

- Workflow – A container (ID: 52925) that groups statuses for the org.

- Status Categories – Fixed categories: 2 = Open/Active, 3 = Closed/Done.

- Workflow Statuses – Named statuses (e.g. “To Do”, “Doing”) assigned to a category.

The sandbox only shipped with two statuses: Open (146494) and Closed (146495). ClickUp’s Tika Go-Live space uses six: backlog, to do, doing, needs review, blocked, done.

### What We Had to Do

- Created 6 new workflow statuses via direct POST to /api/v2/workflow_statuses (bypassing MCP)

- Manually updated productive.config.json with the new status IDs

- The MCP server needed a restart to pick up the config changes

- Key insight: The MCP server has no tool for creating/managing workflow statuses. This is a gap.

Production implication: Statuses MUST be created and config updated BEFORE any task creation begins. Otherwise you get the same retrofitting problem we hit.

## 3. Assignee Limitations

Tasks only accept a single assignee_id. ClickUp supports multiple assignees per task. The MCP server has no concept of multi-assignment.

| ClickUp Assignee | Productive Person ID | Status |
| --- | --- | --- |
| Greg Forsyth | 1065388 | OK – WORKS |
| Alison Mau | 1065445 | OK – WORKS |
| Eoghan Neligan | 1065459 | OK – WORKS |
| Dan Harrison | 1065460 | OK – WORKS |
| Charlotte | Not in Productive | BLOCKER |
| James Boult | Not in Productive | BLOCKER |
| Zoë Lawton | Not in Productive | BLOCKER |
| Michael Timmins | Not in Productive | BLOCKER |

Decision needed: For multi-assignee tasks, choose primary assignee on the Productive task and note others in description. Or use Productive’s followers/watchers feature if available.

## 4. Description Format Gotchas

The MCP server converts Markdown input to HTML before sending to the API. This works, but:

- Descriptions set on create are HTML-encoded; reading them back shows HTML tags in the output

- We embedded ClickUp metadata (“ClickUp Status: X | Assignees: Y”) in descriptions as a workaround for missing status/multi-assignee support

- For production: Descriptions should contain only the actual task content. Metadata should go in proper fields.

## 5. Batch Operations

The productive_create_tasks_batch tool exists but has limitations:

- Doesn’t support task_list_id per task (only default_task_list_id on wrapper)

- Doesn’t support parent_task_id, workflow_status, or labels per task

- Essentially only useful for flat lists of simple tasks

For production: We’ll need individual productive_create_task calls for full-fidelity migration. Rate limit is 100 requests per 10 seconds, so 120 tasks takes ~15 seconds.

## 6. Rate Limiting & Transport

The MCP server has a built-in rate limiter (100 requests/10s sliding window). The bash helper script uses stdio transport with a Python subprocess for the MCP handshake (initialize → notifications/initialized → tools/call). Each invocation spawns a new process, which adds ~0.5s overhead per call.

- Learning: For bulk operations, a persistent connection or direct API calls via curl are significantly faster.

- We used direct curl for workflow status creation because the MCP server has no tool for it.

## 7. Config Dependency

productive.config.json is loaded at startup and cached. Any changes to workflow statuses, task types, or priorities require:

- Updating the JSON file manually or running npm run setup

- Restarting the MCP server

Risk: If config is stale, operations silently degrade (e.g. status updates ignored).

## Summary: MCP Server Gaps & Recommendations

| Gap | Workaround Used | Effort to Fix | Priority |
| --- | --- | --- | --- |
| No workflow status management tools | Direct API calls via curl | Medium – new tool | HIGH |
| Silent failure on unknown status names | Manual config update + server restart | Low – throw error instead of warn | CRITICAL |
| Batch create missing key fields | Individual creates in a loop | Medium – schema update | HIGH |
| Single assignee only | Primary assignee + description note | High – API limitation | WORKAROUND |
| No config hot-reload | Manual restart after config changes | Low – file watcher | WARNING |
| No delete task tool | Direct API call | Low – new tool | WARNING |
| labels not on UpdateTaskSchema | Set on create only | Low – schema update | WARNING |

# Part 2: Production Migration Sequence

The optimal order of operations to one-shot the production Productive.io instance.

The dry run taught us that metadata must be established before task data flows. The sequence below ensures every task is created with full fidelity on the first pass — no retrofitting.

## Phase 0: Pre-Flight Checks

Goal: Validate source data and target environment before touching anything.

- Export full ClickUp workspace hierarchy (all spaces, folders, lists, tasks, subtasks, comments, attachments)

- Verify Productive.io project structure exists (projects, boards, task lists)

- Run productive_list_people and map all ClickUp assignees to Productive person IDs

- Identify any missing people — decide whether to create them or map to alternatives

- Audit ClickUp statuses across all spaces and build the master status map

- Document any ClickUp custom fields that need Productive equivalents

## Phase 1: Metadata Layer

Goal: All reference data in place so tasks can reference it at creation time.

### 1a. Workflow Statuses

- Create all required workflow statuses via API (POST /api/v2/workflow_statuses)

- Map each ClickUp status to a Productive status with the correct category (Open=2, Closed=3)

- Update productive.config.json with new status IDs

- Restart MCP server and verify with a test status update

### 1b. People / Assignees

- Ensure all assignees exist in Productive (create/invite if needed)

- Build the ClickUp username/email → Productive person_id lookup table

- Decide the multi-assignee strategy: primary assignee + description note, or primary + followers

### 1c. Project Structure

- Create any missing projects, boards, and task lists in Productive

- Map ClickUp Space → Project, Folder → Board or Task List grouping

- Verify task list IDs are captured for the creation script

### 1d. Labels & Custom Fields

- Define any labels needed (these CAN be set on create)

- Map ClickUp custom fields to Productive custom fields or task_type/priority

- Update productive.config.json if new task types or priorities are needed

## Phase 2: Task Creation

Goal: All tasks created with full metadata in a single pass.

### 2a. Parent Tasks First

Create all parent (top-level) tasks with:

- title, description (clean — no metadata workarounds)

- project_id, task_list_id

- assignee_id (from Phase 1b lookup)

- workflow_status (from Phase 1a mapping)

- due_date, start_date (if set in ClickUp)

- labels (if applicable)

- priority, task_type (if mapped)

Capture each returned Productive task ID, keyed by ClickUp task ID.

### 2b. Subtasks Second

Create subtasks with parent_task_id referencing IDs from 2a. Same fields plus parent relationship.

### 2c. Checklists / Todos

If ClickUp tasks have checklists, create them via productive_create_todo after the task exists.

## Phase 3: Rich Content

Goal: Comments, attachments, and linked documents.

### 3a. Comments

- For each task with ClickUp comments, create via productive_list_comments / create equivalent

- Note: The MCP server doesn’t currently have a create_comment tool — check if this has been added or use direct API

### 3b. Attachments

- Download from ClickUp, upload via productive_upload_attachment

- Rate limit consideration: large files may need throttling

### 3c. Pages / Docs

- If ClickUp Docs exist, recreate via productive_create_page

- Body format: Markdown input, converted to Productive’s ProseMirror JSON internally

## Phase 4: Relationships & Dependencies

Goal: Task dependencies and cross-references.

- Map ClickUp dependencies to Productive via productive_create_task_dependency

- Types supported: blocks, is_blocked_by, relates_to, duplicates

- Requires both source and target task IDs in Productive (from Phase 2 mapping)

## Phase 5: Verification

Goal: Confirm migration fidelity before declaring success.

- Count tasks in Productive vs ClickUp per space/project

- Spot-check 10% of tasks for correct status, assignee, description, parent/child relationships

- Verify all subtasks are correctly nested

- Check comments and attachments on a sample of tasks

- Run productive_search_tasks with each status to confirm distribution matches ClickUp

## Visual: Migration Sequence

| Phase | Step | Depends On | Tool / Method |
| --- | --- | --- | --- |
| 0 | Export ClickUp data | — | ClickUp MCP |
| 0 | Map assignees | — | productive_list_people |
| 1a | Create workflow statuses | Phase 0 (status audit) | Direct API (curl) |
| 1a | Update config + restart | Status creation | Manual / npm run setup |
| 1b | Create/verify people | Phase 0 (assignee map) | Productive admin / API |
| 1c | Create project structure | — | productive_create_task_list |
| 1d | Configure labels + fields | 1c | Config + API |
| 2a | Create parent tasks | All of Phase 1 | productive_create_task |
| 2b | Create subtasks | 2a (need parent IDs) | productive_create_task |
| 2c | Create checklists | 2a + 2b | productive_create_todo |
| 3a | Migrate comments | 2a + 2b | Direct API / TBC |
| 3b | Upload attachments | 2a + 2b | productive_upload_attachment |
| 4 | Create dependencies | 2a + 2b (both task IDs) | productive_create_task_dependency |
| 5 | Verify migration | All phases complete | Search + spot checks |

## Key Principle

Metadata first, tasks second, rich content third, verify last. Every field on productive_create_task should be populated at creation time. No retrofitting. This was the single biggest lesson from the dry run.